## trustfund_1stQ2017
FDP Form 6- Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS OR ACTIVITIES
FOR THE 1ST QUARTER, CY 2017
Province, City or Municipality: MINA, ILOILO
Program or Project | Location | Total Cost | Date Started | Target | Project Status |  | No. of Extentions, | Remarks
|  |  |  | Completion | % of | Total Cost | if any
|  |  |  | Date | Completion | Incurred to date
Implementation of various | DA-Mina, Iloilo | 600000 | 2015-06-15 | 2017 | 70% | 712615.4 | - | on-going
Grass Roots Proj. under (GRPB) |  | 400000
Integrated Community Food
Production (NAFC)
Construction of Evacuation | Poblacion, Mina | 1000000 | 2016-01-25 | 2016-01-25 | 90% | 973162.28 | - | on-going
2nd Level Motorpool
Construction of Evacuation | Mina West | 500000 | 2016-11-03 | 2017-03-03 | 30% | 353952 | - | on-going
Center- Mina Recreation Center |  | 500000
Construction of Comprehensive | Poblacion, Mina | 1000000 | 11/3/1016 | 2017-03-03 | 90% | 909930.19 | - | on-going
Drainage System
Construction of Mina National | Bargy. Bangac, | 2000000 | 2016-11-03 | 1900-02-18 | 50% | 2000000 | - | on-going
High School-Home Economics | Mina. | 1000000
Building
Rehabilitation of Water Supply | Publacion Mina | 5000000 | 2016-11-03 | 2017-05-03 | 30% | 2246486.5 | - | on-going
System (Phase II)
Mina Subdivision-(Pabahay ng | Publacion Mina | 2000000 | 2016-11-03 | 2017-03-03 | 30% | 300000 | - | on-going
Mina) Site development
Concreting of Mina National | Brgy. Bangac, Mina | 2000000 | 2017-02-15 | 2017-08-15 | 100% | 1846342.3 | - | completed
High School Flag Raising Area
Construction of Municipal Food | Brgy.Cabalabaguan | 1500000 | 2017-03-30 | 2017-09-30 | 70% | 213300 | - | on-going
Terminal(Formerly Bagsakan
Center)
Repair of School Buildings- | Amiroy, Mina | 100000 | 2016-11-05 | 2017-05-31 | 76% | 76290 | - | on-going
Amiroy Elementary School
We hereby certify that we have reviewed the contents and hereby attest
to the veracity and correctness of the data or information contained in
this document.
(SGD.) LICERIO C. PATINGO (SGD.) ELEANOR P. PASUQUIN (SGD.) HON. REY P. GRABATO
MGDH/GSO/ICO-MEO OIC-Municipal Accountant Municipal Mayor