## Sheet1
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2018
MUNICIPALITY OF MINA
Program/ Project/ Activity Description | LOCATION | TOTAL COST | Date Started | Target completion Date | Porject Status |  | No. of Extension, if any | Remarks
[5 empty] | % OF Completion | Total cost incurred to Date
1000 - GENERAL PUBLIC SERVICE
Intensify/Enforcement od RA 9165 and Other Pertinent Laws on Illigal Drugs | MINA, ILOILO | 723463 | JAN. 2018 | DEC. 2018 | 0% | 0
De-clogging/Repair/Maintenance of Drainage Canals | MINA, ILOILO | 400000 | JAN. 2018 | DEC. 2018 | 0% | 0
Rehabilition of Drainage Canal (Public Market) | MINA, ILOILO | 1000000 | JAN. 2018 | DEC. 2018 | 0% | 0
3000 - SOCIAL SEVICES
Site Development for Socialized Housing (Pabahay ng Mina) | MINA, ILOILO | 1000000 | JAN. 2018 | DEC. 2018 | 0% | 0
Acquisition of Lot for Socialized Housing | MINA, ILOILO | 500000 | JAN. 2018 | DEC. 2018 | 0% | 0
Rehab/Improvement of Streetlights Realigned to improvement of Evacuation Center / Recreation center and construction of concrete bleachers | MINA, ILOILO | 2000000 | JAN. 2018 | DEC. 2018 | 14.98% | 299619.98
Development/Improvement of Municipal Plaza | MINA, ILOILO | 1500000 | JAN. 2018 | DEC. 2018 | 0% | 0
8000 - ECONOMIC SERVICES
Rehabilitation & Improvement of 116.064 kms. FMR in all Barangays | MINA, ILOILO | 500000 | JAN. 2018 | DEC. 2018 | 79.85% | 399230.1
Rehabilitation of Municipal Nursery | MINA, ILOILO | 60000 | JAN. 2018 | DEC. 2018 | 0% | 0
Repair/ Improvements of Water Systems | MINA, ILOILO | 70000 | JAN. 2018 | DEC. 2018 | 0% | 0
Purchase of Heavy Equipment | MINA, ILOILO | 3500000 | JAN. 2018 | DEC. 2018 | 0% | 0
Construction of MRF with Coposting Facilities (Public Market) | MINA, ILOILO | 150000 | JAN. 2018 | DEC. 2018 | 0% | 0
Rehabilitation/Repair of Public Market (stall, ceiling, cubicles, pipeline, public CR) | MINA, ILOILO | 150000 | JAN. 2018 | DEC. 2018 | 0% | 0
9000 - OTHER SERVICES
REPAYMENT OF Loan A,ortization with the World Bank through Logofind for MNHS, Health Center, Elevated Water Tank from NHA and DMAF Loan for MSTC | MINA, ILOILO | 2415807 | JAN. 2018 | DEC. 2018 | 18.41% | 444650.56
Other Development Projects | MINA, ILOILO | 500000 | JAN. 2018 | DEC. 2018 | 20% | 100000
TOTAL================================================ |  | 14469270 |  |  | 8.594% | 1243500.64
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information
contained in this document.
Prepared by: | [5 empty] | Noted by:
(SIGNED) |  | (SIGNED) |  |  |  | (SIGNED)
EDUARD V. PASTOLERO |  | ELEANOR P. PASUQUIN |  |  |  | HON. REY P. GRABATO
LRCO 1 |  | OIC - Municipal Accountant |  |  |  | LCE / Municipal Mayor