## Sheet1
FDP Form 6- Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS OR CTIVITIES
FOR THE SECOND QUARTER CY 2018
Province, City or Municipality: MINA, ILOILO
Program or Project | Location | Total Cost | Date Started | Target | Project Status |  | No. of Extentions, | Remarks
|  |  |  | Completion | % of | Total Cost | if any
|  |  |  | Date | Completion | Incurred to date
Implementation of various | DA-Mina, Iloilo |  | 2015-06-15 |  | 81% | 807317.1 | - | on-going
Grass Roots Proj. under (GRPB) | 1st Tranche | 600000
Integrated Community Food | 2nd Tranche | 400000
Production (ICFP)
Construction of Evacuation | Poblacion, Mina | 1000000 | 2016-01-25 | 03/25/2016 | 97% | 973160.28 | - | on-going
2nd Level Motorpool
Construction of Evacuation | Mina West | 2000000 | 2016-11-05 | 2017-10-31 | 67% | 1348968.99 | - | on-going
Center- (Mina West)
Construction of Evacuation | Poblacion, Mina | 2000000 | 12/16/2017 | 4/16/18 | 15% | 299829.62 | - | on-going
Facility- (MRC)
Rehabilitation of Water Supply | Publacion Mina | 5000000 | 2016-11-03 | 2017-05-03 | 90% | 4494043.56 | - | on-going
System (Phase II)
Concreting of Road (Bangga | Tumay, Mina | 2000000 | 2/16/2018 | 3/31/2018 | 99% | 1978962.63 | - | on-going
Penaflorida)
Concreting of Road (Highway to | Cabalabaguan, | 3000000 | 2/26/2018 | 4/7/1018 | 98% | 2938883.34 | - | on-going
MPC) Barangay Road | Mina
Concreting of (Bangga 13 to | Mina East, Mina | 5000000 | 2/26/2018 | 4/17/2018 | 98% | 4897296.26 | - | on-going
Banga Suarez Road)
Repainting of Municipal Bldg. | Poblacion, Mina | 350000 | 2018-04-15 | 2018-05-31 | 71% | 249895 | - | on-going
Establishment of Material
Recovery Facility/Purchase of | Mina, iloilo | 427500 | 2018-04-15 | 2018-07-15 | 47% | 202788 | - | on-going
Equipment
We hereby certify that we have reviewed the contents and hereby attest
to the veracity and correctness of the data or information contained in
this document.
(SIGNED) |  | (SIGNED) |  |  |  | (SIGNED)
LICERIO C. PATINGO ELEANOR P. PASUQUIN HON. REY P. GRABATO
MGDH/GSO/ICO-MEO OIC-Municipal Accountant Municipal Mayor